## Actions
Potential Actions to Increase Efficiencies in Permitting Restoration
|  |  | Themes |  |  | Tactical Approach(es) |  |  |  | Duration | [5 empty] | Guidance
| ID # | PROPOSED ACTION ITEM | 1 | 2 | 3 | Under Existing Authority | Regulatory or Administrative Change | Governor's Executive Order | New Legislation/ Statutory Change | 3-6 mo | 6-12 mo | 1-1.5 yrs | 1.5-2 yrs | 2-2.5 yrs | beyond | Interdependencies/Critical Paths/Linkages | Key People to Engage? | Input from Previous Roundtables and Meetings
| 1 | Work with SWRCB to ensure new Habitat Restoration 401/WDR pathway is completed, meets the needs of practitioners, and that their companion CEQA effort results in a programmatic document that can be used by other project proponents. | 401/WDR & CEQA | Programmatic Permits | Aquatic Habitat Restoration |  | In progress | can support |  |  |  |  | X (reg / admin change) |  |  | Coordination with Army Corps | SusCon | Maybe consider pre-approved organization for conditions? Would benefit from general EO support. good progress to-date. New wetlands policy has a streamlined 401 process for ecological restoration and enhancement projects; too early to tell if it will be implemented. Programmatic doc is the next steps - can further streamline. New policy and 401 permit process CAN be implemented effectively under existing authority - will it be? Prog doc will require reg or admin change.
| 2 | Create unified permit application (ideally, on-line) for existing, and potentially any new, Small Habitat Restoration pathways including 401/WDR and HREA | 401/WDR & F&G Code | Small Habitat Restoration (Improve) | Permit Applications | Joint effort under existing authority (SWRCB and CDFW)- |  | X |  |  |  | X (existing authority) |  |  |  | 3, 23, 28, 29 |  | Broaden scope to all state purview/agencies. Yes! it is doable. EO to start and make it happen. How to prevent backsliding and not become like JARPA with limited value and ownership.
2 | 3 | Eliminate or modify the 500 linear foot cap on existing SWRCB and DFW restoration compliance processes (Cat Ex 15333 original 5 acre limitation would still be in palce) | 401/WDR & F&G Code | Small Habitat Restoration (Improve) | Modify Existing Regulations |  | Remove or expand 500 linear foot cap through current update and re-authorization process (SWRCB) |  |  | X (reg / admin change) | X | ? |  |  |  | 2, 23, 8, 10, 33 | Phil Crader, Paul Hann (SWRCB) | Where did 500 lf come from? Possibly modify to tiered system. Sink with grant programs. Ramifications outside of restoration projects? Restoration specific programs, seperate to encourage large scale work. Well supported by the table and achievablle. Specific to vision and species.
| 4 | Ensure planning efforts such as RCIS/TMDL/ NCCP/Recovery Plans more effectively "cut green tape" by incentivizing implementation actions though regulatory efficiencies. | 401/WDR & F&G Code | Existing Tools | Programmatic Permits | Existing NCCPs include coverage (and fee waiver) for restoration/ stewardship activities | CDFW and SWRCB develop new pathways under RCIS, TMDL, and Recovery Plan to increase pace and scale of project that implement the goals of the plan | EO to support this action |  |  | X (existing authority) |  | X (reg / admin change) | X (reg / admin change) |  |  |  | guidance/training for staff: translating tmdl into permit fees and different approach for bonafide restoration. Some of these programs don't currently fit this incentive models.
| 5 | Create programmatic permits for restoration/ stewardship activities carried out by the state (including coverage for State-funded projects). | 401/WDR & F&G Code (etc) | Programmatic Permits | Restoration Actions by Regulatory/ State Agencies |  | New Programmatic permits/authorizations developed to cover projects (CESA, 1600, 401/WDR, etc) | EO to support this action - INCLUDE SPECIFICALLY AS BULLET PNT. | Possible need to give CDFW authority to do general permits in F&G code |  | X (EO) |  | X (reg / admin change) |  |  | 1,11,12,14,19, 24,25,27, 33
| 6 | Eliminate redundancy between 401/WDR process and Construction General Permit NPDES process for restoration actions that require a 401/WDR. | 401/WDR | Clarify Existing Regulations | Redundancy | Requires CalEPA/SWRCB directive - IN PROGRESS? |  |  |  |  | X (existing authority)
| 7 | Secure clear interpretations by CNRA and OPR on specific language in CEQA Cat Ex Class 33 that will result in the exemption being fully utilized by lead agencies and consultants (e.g. confusion regarding "significant impact to special status species and "primarily with hand-labor.") | CEQA | Small Habitat Restoration (Inprove) | Clarify Existing Regulations | PREFERRENCE: Use Director's Bulletin or Secretary's Order to clarify language and intent in Cat Ex Class 33 to enable full utilization(CNRA). -AND/OR- Clarify intent through update/re-authorization of SWRCB Permit (SWRCB) | Modify language in Cat Ex through Administrative Process of annual guidelines Update (OPR) |  |  | X (existing authority) | X (admin change) | X (budget) |  | X? |  | 8 | Suscon has tried to do and can help? OPR
3 | 8 | Expand the 5-acre limit on CEQA Cat Ex Class 33 and associated pathways | CEQA | Small Habitat Restoration (Expand) | Modify Existing Regulations | Use Director's Bulletin or Secretary's Order to clarify language and intent in Cat Ex Class 33 to enable full utilization(CNRA). -AND/OR- Clarify intent through update/re-authorization of SWRCB Permit (SWRCB) | Expand acreage of Small Habitat Restoration Exemption |  | Propose new or work with another currently proposed CEQA amendment | X (existing authority) | X (reg / admin change) | X (new leg/statutory change) |  | X? |  | 7 | OPR | Needs off ramps and 1st need to do an analysis
| 9 | CEQA statutory exemption for restoration and stewardship activities. | CEQA | Restoration Actions by Regulatory/ State Agencies | Statutory Exemption |  |  |  | Propose new Statutory Exemption to Cover Restoration Projects (?) | [5 empty] | X (new statute) |  |  | Love it but not likely, due to political feasibility and basically requires full CEQA reform. Needs more definition and side board. Maybe sample language from NRCS NEPA. Could avoid bottleneck of lead agency.
3 | 10 | Amend language in Cat Ex Class 7 & 8 to exclude ecological restoration projects from definition of "construction" | CEQA | Restoration Actions by Regulatory/ State Agencies | Modify Existing Regulations |  | CEQA Guidelines changes re: Exemptions 7 & 8 for beneficial restoration to include habitat restoration actions (CNRA thru OPR request) |  | Modify language in Cat Ex 7 & 8 exclude ecological restoration projects from definition of construction |  | X (reg / admin change) | X (budget) | X (statutory change) |  |  | 8,9, 11, 12 | OPR | For 10, 11, 12 - GOOD APPROACH WITH TIMELINE. Concern about oversight from other agencies that might want oversight when projects are exempt. Who are state champions. Think and define vocab.
5 | 11 | Programmatic CEQA coverage for restoration/ stewardship activities carried out by the state (including coverage for State-funded projects). [note potential overlap/redundancy with recommended action items for Cat Ex Class 7 and 8] | CEQA | Restoration Actions by Regulatory/ State Agencies | Programmatic Permits |  | New Programmatic document | EO to support this action | Could be achieve through new statute or legislation |  |  |  | X (reg / admin change) |  | X (new legislation) | 8,9,10,12
11 | 12 | Develop a Certified Regulatory Program(s) (similar process to a Timber Harvest Plan) to provide a CEQA equivalent document for landcape scale restoration and stewardship actions. | CEQA | Restoration Actions by Regulatory/ State Agencies | Programmatic Permits | Possible | Possible | EO to support this action |  | X (EO) |  | X (existing authority) | X (reg / admin change) |  |  | 10,11 |  | Long-term performance meausres for short term impacts (show net benefit).
| 13 | Require State agencies acting as CEQA leads to follow CEQA timelines (concern is letting the process go to long). | CEQA | Restoration Actions by Regulatory/ State Agencies | Timelines | Yes, through directive |  | ? |  |  | X (existing authority)
10 | 14 | Develop efficiencies for Coastal Commission, BCDC , and Delta Stewardship Council (i.e. could be linked to small habitat restoration and/or larger restoration efforts through Federal Consistency with new USFWS BO) | Coastal Act/ Coastal Zone Management Act | Small Habitat Restoration (Expand) | Programmatic Permits | PREFERENCE: Possible | Possible | EO to support this action | Possible | X (EO) | X (existing authority) | X (reg / admin change) |  | X (new leg) |  | 33,15, 17,31,32,35 | Dept Finance? | Developing an inter agency review process for coastal zone projects. See AB1282 recommendations. Too broad, include specifics like creating a parallel proccess or waiver for projects that fall under Cat Ex 15333 AND evaluate Fed Consistency for upcoming USFWS BO. Increase coordination and include Commission. Evaluate PRC 30411 . Delta Stewardship Council is in the process of developing new procedures to streamline permitting of beneficial projects.
| 15 | Develop federal consistency determination with the Coastal Act for the new USFWS Programmatic Biological Opinion for restoration projects. | Coastal Act/ Coastal Zone Management Act | Programmatic Permits | State and Federal | Requires federal agencies to request Consistency | [5 empty] | X (existing authority)
12b | 16 | Create an exemption in the Coastal Act to enable vegetation management for fuel load reduction | Coastal Act/ Coastal Zone Management Act | New Exemption |  | Collaborate with CalFire and CDFW |  |  | Requires amendment to Coastal Act, would be link to urgency re: wildfire |  |  |  |  | X (new leg) |  |  |  | Existing authority (Commission) and collaborate with CalFire. Not needed by consider as a model.
| 17 | Executive Order to prioritize permit efficiencies (‘directive from the top’) | Executive Order | Habitat Restoration |  | Yes, critical to setting stage for CGT across agencies |  | Executive Order to Recitals to (a) outline urgency, (b) clarify progress to date, (c) define beneficial restoration and (d) require agency alignment |  | X (EO) | [6 empty] | Suscon | Add specifically to EO: direct agencies to prioritize implementation of restoration, develop and UTILIZE expedition permitting for restoration, and coordinate funding sources. Include $ for agencies to implement actions (EO provide budget justifcations). Encourage agencies to structure restoation in 1 unit so above can be coordinated (Process, $, Partnering).
15 | 18 | Ensure better utilization of existing permit streamlining tools such as Voluntary Local Program (VLP) and Safe Harbor (SH) | F&G Code | Existing Tools | Programmatic Permits | These regs are already on the books and require a committment to efficient development, utilization, etc (CNRA). | Deeper dive could be possible, depends on changes. |  |  | X (existing authority) |  |  |  |  | Feds -3yrs or more; State 2-3 years | 19, 28, 29, 2, 17 |  | investigate if VLP can be better used. SOCIAL CHANGE. Cal HR, LEAN6Sigma, VLP to remove exclusion for fish?
12 | 19 | Create CDFW Statewide Permit for Habitat Restoration Projects (CESA & 1600, companion to new 401/WDR for project that do not fit under HREA) | F&G Code | Programmatic Permits | Aquatic (All?) Habitat Restoration | Utilize existing pathway such as master permit, with Director approved fee reduction. | Develop new pathway similar to process of programmatic cannabis approvals |  | Create new program within F&G code 1600 & CESA, specifically for habitat restoration projects that are larger than HREA projects |  | X (existing authority) | X (reg / admin change) |  | X (statutory change) |  | 1,20 |  | Need a reduced fee structure to accompany the permit. Yes. Expands the scope! Need CDFW to particpate.
| 20 | Create funding source to enable reduced fee structure (ideally free) for F&G Code 1600 Agreements for Restoration Projects (HREA and non-HREA) | F&G Code | Fees | Funding |  |  | Include in E.O on CGT |  |  |  | X (budget) | [5 empty] | Add BCDC and CCC fees. Combine 19 and 20
| 21 | Incorporate Fully Protected Species into CESA to reduce barriers to species recovery | F&G Code | Fully Protected Species |  |  | Possible? |  | Likely would require new legislation dissolving FP and incorporating into CESA OR get take provisions in FPS code and mitigate for take |  |  |  |  | X (new leg) |  |  | Environmental NGOs need to see conservation benefit | Leg to authorize take of FP species for restoration (added as new action #39)
| 22 | Indemnify private landowners for unforeseen impacts resulting from implementation of restoration or conservation actions (e.g. Oregon and Washing both have legislation) | F&G Code | Liability |  |  |  |  | In progress -AB2518 (statutory change through Fish and Game Code) |  |  |  | X (amended statute)
| 23 | Secure clear interpretations by CDFW on inclusion of coverage for fully protected species under HREA | F&G Code | Small Habitat Restoration (Improve) | Clarify Existing Regulations | Director's Bulletin (CDFW) | POSSIBLE - Require rulemaking (?) to avoid underground regulation |  |  | X (existing authority) | [5 empty] | 2,3
14 | 24 | Create programmatic CESA compliance as companions to federal programmatic Biological Opinions (NOAA Restoration Center and USFWS) for restoration projects through use of 2081(a) for statewide or regional CDs or MOUs. | F&G Code | Programmatic Permits | Existing Tools | CDFW to utilize consistency determination or MOU | POSSIBLE- need to promulgate new regulations through F&G Code to create efficiency? |  |  |  | X (existing authority) |  | X (reg / admin change) |  |  | 25 |  | Need to get feds to "request" CD process. CDFW taking leap of faith by accepting fed BO. Need to address fully mitigated and financial assurances pieces of CESA and if they actually should apply to restoration projects?
| 25 | Extend CDFW's programmatic permits for its Fisheries Restoration Grant Program to non-FRGP funded habitat restoration projects. | F&G Code | Existing Tools | Programmatic Permits | Enable non-FRGP funded projects that meet the goals and criteria articulated in the programmatic permits for FRGP to be covered under those permits | Enable non-FRGP funded projects that meet the goals and criteria articulated in the programmatic permits for FRGP to be covered under those permits |  |  | X (existing authority) | X (admin change) |  |  |  |  | 24
8 | 26 | Develop statewide approach to facilitate local/county restoration permitting (e.g increase levers/incentives to engage local government participation in SB 375) | Local Permits/ Approvals | Habitat Restoration | Legislation |  |  | Include language in E.O. for CGT that references need to align State and Local regs and policy | Create legislation to incentive/mandate local permitting agencies to create new pathways for restoration and stewardship work | X (EO) |  |  |  |  | X (new legislation) | 5
3 | 27 | Create dedicated funding source for restoration focused agency staff (planning, permitting, funding) | Regulatory Process | Coordination | Funding |  | Adminstrative | EO to support this action? |  | X (EO) |  |  | X (budget) |  |  |  |  | Planning makes it challenging and broadens the amount agencies.
| 28 | Develop a single unified permit application for all State agencies with regulatory authority over restoration/stewardship. Include clear direction/ accountability that the mandate is to increase pace and scale of restoration/ stewardship. | Regulatory Process | Coordination | Permit Applications | Accomplished through MOU between agencies and with a working group (based on JARPA concept) |  | EO to support this action | May require new legistlation? |  |  | X (existing authority) |  |  | XXX | 2,29, 17 |  | very challenging to get 1 hail mary
| 29 | Make all permit applications and status information available online | Regulatory Process | Coordination | Permit Applications | requires funding and administrative will |  | EO to support this action |  |  |  |  | X (existing authority) | X |  | 2, 28 |  | easy option, needs money.
| 30 | Elevate role and opportunity for trusted regional entities (RCDs, Conservancies, land trusts) to drive regional restoration collaboration, investments, compliance and function as permit ambassadors (expanded PIR concept) | Regulatory Process | Coordination & Culture | Regional/Local Agencies | Various mechanisms |  | EO to support this action? |  | X (EO) |  | X (existing authority) | [5 empty] | Consider specific staff at agencies. Gap analysis or regions and RCD for investment and collaboration.
7 | 31 | Increase internal coordination between technical staff (environmental scientists, engineers), permit staff, and funding staff at intra- and inter-departmental levels to improve efficiency of project delivery. Include clear direction/ accountability that the mandate is to increase pace and scale of restoration/ stewardship. | Regulatory Process | Coordination & Culture | Strike-teams | Coordination among technical, compliance and funding staff (CNRA lead, multi-department) |  | Include language in E.O. for CGT that references re-org to address Climate Crisis |  | X (EO) |  | X (existing authority) |  |  |  | 32,33, 35 | AB1282 TAC | Identiify clear shared goals, expectations and accountability. Annual/bienniel
| 32 | Create inter-agency (state or state-fed-local) restoration implementation "strike teams" to facilitate efficient and expedited inter-agency communication, review, feedback, and approval (e.g. IWRP, [Integrated Watershed Restoration Program of Central Coast], BRITT, Corps Inter Agency Mtgs, etc). Include clear direction/ accountability that the mandate is to increase pace and scale of restoration/ stewardship. | Regulatory Process | Coordination & Culture | Strike-teams | Regional/statewide interagency collaborative compliance teams (CNRA lead, multi-department) + MOU |  | Include language in E.O. for CGT that references re-org to address Climate Crisis |  | X (EO) |  | X (existing authority) |  |  |  | 31,33, 35 | AB1282 TAC | federal agency coordination/cooperation. MOUs?, Need to tie in Federal Compliance. STEP 1, determine lead --> Resources Agency
| 33 | Evaluate potential for creating a separate "track" or process for permitting restoration conservation work across state agencies | Regulatory Process | Coordination & Culture | Strike-teams |  | Possible | LINK | Possible, depending on need to codify and clarify roles and responsibilities |  |  | X (reg / admin change) | X (new leg) |  |  | 31,32, 35, 38 | Suscon has model language. | Thinking across the state. Permit, funding, process for restoration on sep track -- creates more partnerships and incentives. Consider inclusion of mitigitation (off-side)
| 34 | Require new permitting staff to apply for all local, state, and federal permits for at least one restoration project. | Regulatory Process | Culture |  | Yes |  |  |  | X (existing authority)
13 | 35 | Develop clear guidance from the State on regulatory agency jurisdiction for habitat restoration activities with clear direction on addressing overlapping jurisdiction (geographic and content) and a process to reduce redundancy and designate 1 lead agency | Regulatory Process | Coordination | Overlapping Jurisdications |  | Develop working group to define issue and provide an administrative remedy (CNRA w/CalEPA) | Ex Order could highlight creating efficiencies through reduction in redundancy | New statute with process and guidance designating a primary lead agency for restoration projects |  |  | X (admin change) |  |  | X (new legislation) | 33, 14 |  | (regulatory or statutory?) change required for enabling. Consider inclusion of mitigitation (off-side)
| 36 | Ensure that new environmental and administrative pathways or policies are reviewed to avoid intentional or unintentional regulatory action that will create new barriers. | Regulatory Process | Coordination & Culture | Unintended Consequences | Potential increase coordination early in leg process | [11 empty] | would reduce silos that are "required" with other agencies.
| 37 | Create new efficiencies in Water Rights Permits to expedite implementation of projects that result in increased ecological stream flows and groundwater recharge | Water Rights | Regulatory Process | Programmatic Permits | Guidance for SWRCB staff that they have discretion to create metrics for these types of projects | Possible | EO to support this action |  | X (EO) | X (admin change) | X (regulatory change) | [5 empty] | Needs staff and IT for making instituational change to streamline; which allocation coming from??; duration great than 2+ years.
| 38 | Reduce redundancy/green tape by utilizing CEQA compliance as a permit equivalent process for other state environmental regulations (e.g. CEQA documents contain all or most elements/requirements of individual permits and state agenices review these docs as responsible agencies, why require permits in addition?) | CEQA | Overlapping Jurisdictions | Redundancy |  | Increased emphasis of role of responsible agency | EO to support this action? | Might require new legislation or statute change in F&G Code, Coastal Act, Water Code, etc. to increase utilization of CEQA as permit equivalent document. | X (EO) |  | X (admin change) | X (new leg) |  |  | 33 |  | Early coordination on development of CEQA review to come to agreement/MOU. Build a permit process that relies on a good CEQA review, good CEQA doc --> should be easy to get permit.
1 | 39 | Legislation to authorize take of Fully Protected Species for restoration projects. | F&G Code | Fully Protected Species |  |  |  |  | Likely would require modification to existing FP statute | [6 empty] | 21
| 40 | Directory of programmatic permits and docs all posted in one place. | Programmatic Permits | Outreach |  | Yes | [11 empty] | List of all restoration specific programmatics on Sustainable Conservations website. https://suscon.org/wp-content/uploads/2019/07/Sustainable-Conservation-Expedited-Permitting-Summary-Table-7-17-19.pdf
| 41 | Allow state grant funded projects to utlilize those funds as meeting "finanical assurances" for CESA take. | F&G Code | CESA | Costs | Possible, if through use of MOUs/2081(a) | ? | [8 empty] | 24 |  | Curently in-process with Redwoods Rising. F&G Code 2081(a) Through permits or memorandums of understanding, the department may authorize individuals, public agencies, universities, zoological gardens, and scientific or educational institutions, to import, export, take, or possess any endangered species, threatened species, or candidate species for scientific, educational, or management purposes
12a | 42 | Implement PRC 30411, which directs the Coastal Commission to... "not establish or impose any controls with respect thereto [wildlife and habitats under the jurisidction of CDFW) that duplicate or exceed regulatory controls established by these agencies" | Coastal Act/ Coastal Zone Management Act | Overlapping Jurisdictions | Redundancy | Yes | [9 empty] | 14,15,16 |  | Public Resources Code 30411: The Department of Fish and Wildlife and the Fish and Game Commission are the principal state agencies responsible for the establishment and control of wildlife and fishery management programs and the commission shall not establish or impose any controls with respect thereto that duplicate or exceed regulatory controls established by these agencies pursuant to specific statutory requirements or authorization
| 43 | Modify the SWRCB's 401/WDR for Small Habitat Restoration Projects and CDFW's HREA to enable use by off-site mitigation projects. | 401/WDR & F&G Code | Small Habitat Restoration (Expand) | Mitigation | Possible | Possible, during update of 401/WDR in 2020 | [8 empty] | 2, 3, 23, 28, 29